## Sheet1
|  |  | Tester: glafrance | Tester: glafrance | Tester: glafrance | Tester: glafrance | Tester: glafrance | Tester: glafrance
|  |  | Build Number: c129568 | Build Number: c887516 | Build Number: 5df92a8 | Build Number: f6a109f | Build Number: b741424 | Build Number: f8eaee2
|  |  | Test Date: 11/1/2015 | Test Date: 11/8/2015 | Test Date: 11/15/2015 | Test Date: 11/22/2015 | Test Date: 11/22/2015 | Test Date: 11/30/2016
|  |  | Pass Rate: | Pass Rate: | Pass Rate: | Pass Rate: | Pass Rate: | Pass Rate:
Type | Req. Number | Requirement Text | 45.1% | 72.55% | 84.31% | 90.2% | 94.12% | 100%
System Environment |  | FitApp system will consist of a web portal where users (actors) have their own accounts to input their data in and retrieve statistics and graphs to analyze their input. The web portal will communicate with the database to store and retrieve users’ data.
| 1 | A user has an account | p | p | p | p | p | p
| 2 | A user can input data | p | p | p | p | p | p
| 3 | A user can see their own data | p | p | f | p | p | p
System Function |  | Users of FitApp will be able to input data such as amount of calories consumed, number of hours slept, number of steps taken. The system will in return provide the users with analysis of their input and based on that will provide some tips on how to improve the wellness of the users.
| 4 | A user can input calories consumed | f | p | p | p | p | p
| 5 | A user can input hours slept | f | p | p | p | p | p
| 6 | A user can input steps taken | f | p | p | p | p | p
| 7 | A user can see analysis of their input | f | p | p | p | p | p
User Types |  | The system has 1 type of users only; FitApp users. However, some users can access general data without the need to have a personal account (read nutrition and wellness articles and tips, view general statistics)
| 8 | Any user can read nutrition/wellness articles | f | f | p | p | p | p
| 9 | Any user can view general statistics | f | f | p | p | p | p
Interface |  | The FitApp site will map to the sitemap in the requirements document
| 10 | The site has an account page | f | f | p | p | p | p
| 11 | the site has a profile page | p | p | p | p | p | p
| 12 | the site has an analysis page | f | p | p | p | p | p
| 13 | the site has a nutrition page | f | p | p | p | p | p
| 14 | the site has an exercise page | f | p | p | p | p | p
| 15 | the site has a general statistics page | f | f | f | f | p | p
| 16 | the site has a contact page | f | f | p | p | p | p
Signup |  | FitApp should allow new users to sign up or register
| 17 | A first time user of FitApp website will be directed to a page to register. | p | p | p | p | p | p
| 18 | The user will get a form to fill with basic information such as (Name, email, password, Date of Birth). | p | p | p | p | p | p
| 19 | The form will be submitted to the FitApp database and the user’s new profile will be created. | p | p | p | p | p | p
Login |  | FitApp should allow registered users to login to their accounts and reset their passwords if forgotten
| 20 | Current users can click on the Account link to log in to their accounts | p | p | p | p | p | p
| 21 | They will be given a form to input their email and password. | p | p | p | p | p | p
| 22 | Upon successful verification of the email and password from the FitApp database the user will be granted access to their account. | p | p | p | p | p | p
| 23 | If the user forgot their password they have the choice to click on “forgot your password?” link and be sent a password reset email. | f | f | f | p | p | p
Input Data |  | FitApp should allow registered users to input wellness personal data to their accounts
| 24 | Users who have already logged in to their accounts can go the Input personal data page. | p | p | p | p | p | p
| 25 | The users will be given a form to input information. They will also be able to specify the times of these input data points. | f | p | p | p | p | p
| 26 | The users input is optional, if they don’t wish to input all information no error will be generated. | f | p | p | p | p | p
| 27 | All input will be sent to FitApp database and stored there with timestamps to track changes. | p | p | p | p | p | p
Analysis |  | FitApp should allow registered users to retrieve analysis and graphs of their input wellness personal data
| 28 | Users who have already logged in to their accounts can go the Analysis page. | p | p | p | p | p | p
| 29 | The analysis page will display a group of graphs analyzing the user’s input change over time. | p | p | p | p | p | p
| 30 | The user can specify the analysis to be a weekly view/monthly view/yearly view. The can choose the specific week or month to view the change during that time. | p | p | p | p | p | p
| 31 | The page will also display tips for the user to improve their wellness. | f | f | p | p | p | p
General Info |  | FitApp should allow all users (registered and non-registered) to view general information and articles of nutrition and exercise in addition to anonymous general analysis of all FitApp users
| 32 | All FitApp users can access the General statistics page showing analysis and statistics on FitApp users. | f | f | f | f | p | p
| 33 | The page will provide analysis on the average input data points of FitApp users and their change | f | f | p | p | p | p
| 34 | The analysis will be anonymous so it will not affect the privacy of FitApp users. | f | f | p | p | p | p
| 35 | All FitApp users can access the nutrition page displaying articles and tips on nutrition. | f | p | p | p | p | p
| 36 | All FitApp users can access the exercise page displaying articles and tips on exercise. | f | p | p | p | p | p
Non Functional |  | Non Functional Requirements
Availability | 37 | This site’s downtime during any day shall not exceed 1 minute. | p | p | p | p | p | p
Usability | 38 | The site will be complete, and each hyperlink and button will lead to a tested event. | f | p | p | p | p | p
| 39 | The site must allow for blank input, to support the case where the user chooses not to share a category of fitness/wellness data. | f | p | p | p | p | p
| 40 | The site will adhere to the “3 click” rule, where each the sitemap is 3 or fewer layers | p | p | p | p | p | p
Financial | 41 | The site will have a budget of $0. | p | p | p | p | p | p
Schedule | 42 | The site will be complete by December 7, 2015 | p | p | p | p | p | p
| 43 | The site will undergo a phase 1 review, and will display a completed skeleton on October 19, 2015. | p | p | p | p | p | p
| 44 | The site will undergo a phase 2 review, with input and trend analysis complete on November 16, 2015. | p | p | p | p | p | p
Security | 45 | The site will keep user data secure by requiring a username and password | p | p | p | p | p | p
| 46 | The website will enforce users to use strong complex password such as a minimum of eight characters, including at least one uppercase letter and one number which will help to protect their information against brute force password guessing. | f | p | p | p | p | p
| 47 | The passwords will not be stored in FitApp databases in the clear, instead, a hash of the password will be stored along with a salt to prevent any leakage of information and secure the password of the users. | f | f | f | p | p | p
| 48 | The site will be secure against SQL injections | f | f | f | f | f | p
| 49 | We can easily prevent this by using sanitized queries when we create the database for the website. | f | f | f | f | f | p
| 50 | We will use messages like “Incorrect username or password” without any details about the query to prevent an attacker from trying brute force attack to get information from error message gives away when one of the fields are correct then the attacker knows he has one of the fields and can find the way to attack the database . | p | p | p | p | p | p
| 51 | Cross site scripting is when an attacker tries to pass in scripting code into a web form and we can prevent it by sanitize any user input before it is processed. | f | f | f | f | f | p
Build-specific Tests |  |  | Note: many of these failures are due to the lack of secondary pages, and that the ability to input data is not available from the profile page. |  | BUG - new users can see the data of a previously logged on user.